## Implementation Plan
CRAYCARE CAPSTONE IMPLEMENTATION PLAN
Activity | Status | Start Date | End Date | Duration (Days) | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[5 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Phase 1: Preliminary Investigation and Requirements Gathering | Completed | 2026-04-06 | 2026-04-30
Phase 2: Chapters 1-3 and Prototype Development and Defense | Completed | 2026-05-04 | 2026-07-26
Phase 3: Construction and Setup of Manual and IoT-Based Tanks | Completed | 2026-08-03 | 2026-08-21
Phase 4: Hardware Assembly, Sensor Calibration, and IoT Integration | In Progress | 2026-05-21 | 2026-09-30
Phase 5: Mobile Application and Cloud Backend Development | In Progress | 2026-05-21 | 2026-09-30
Phase 6: Machine Learning Anomaly Detection Development and Testing | In Progress | 2026-08-03 | 2026-09-30
Phase 7: Actual Tank System Installation and Initial Testing | Pending | 2026-09-24 | 2026-09-30
Phase 8: Sensor Data Collection and System Evaluation | Pending | 2026-10-01 | 2026-11-30
Phase 9: Data Analysis and Chapter 4 Development | Pending | 2026-10-01 | 2026-12-07
Phase 10: Chapter 5 and Final Deliverables | Pending | 2026-11-30 | 2026-12-31

## Milestones & Status
CRAYCARE MILESTONES & STATUS
Milestone | Target Date | Status | Related Phase | Expected Output | Remarks
Official title approval | 2026-04-30 | Completed | Proposal | Approved CrayCare title | Foundation for Chapters 1-3
Submission of Chapters 1-3 | 2026-05-31 | Completed | Documentation | Complete proposal manuscript | For adviser/panel review
Working proposal prototype | 2026-07-12 | Completed | Prototype | Hardware and mobile demo | Ready for proposal defense
Final proposal defense | 2026-07-17 | Completed | Defense | Panel evaluation and corrections | Corrections tracked in plan
Final hardware calibration and tank integration | 2026-09-30 | In Progress | Implementation | Calibrated and fully integrated tank hardware | Final build, wiring, casing, and validation continue in September
Deployment-ready CrayCare system | 2026-09-30 | In Progress | Software | Production-ready app, cloud, feeder, actuators, and alerts | Required before actual tank deployment
ML supporting feature validation | 2026-10-07 | Pending | Machine Learning | Validated anomaly-detection results | Advisory feature; not direct actuator control
CrayCare deployed to actual tank | 2026-09-30 | Pending | Deployment | Operational system installed in the actual tank | Live implementation begins in October
Integrated field-tested system | 2026-11-30 | Pending | Testing | Live-operation, field-test, and usability evidence | Two-month live operation (October-November) plus field-test and usability evidence
Chapter 4 completion | 2026-12-07 | Pending | Documentation | Results and discussion | Based on live system and evaluation data
Chapter 5 and full manuscript | 2026-12-13 | Pending | Documentation | Complete Chapters 1-5 | Ready for final review
Final oral defense | 2026-12-20 | Pending | Defense | Final presentation and panel feedback | Prepare system demonstration
Final submission and closure | 2026-12-31 | Pending | Closure | Approved bound manuscript and archive | Close project records

## Lists
Status | Phase
Completed | Phase 1: Preliminary Investigation and Requirements Gathering
In Progress | Phase 2: Chapters 1-3 and Prototype Development and Defense
Pending | Phase 3: Construction and Setup of Manual and IoT-Based Tanks
For Evaluation | Phase 4: Hardware Assembly, Sensor Calibration, and IoT Integration
Phase 5: Mobile Application and Cloud Backend Development
Phase 6: Machine Learning Anomaly Detection Development and Testing
Phase 7: Actual Tank System Installation and Initial Testing
Phase 8: Sensor Data Collection and System Evaluation
Phase 9: Data Analysis and Chapter 4 Development
Phase 10: Chapter 5 and Final Deliverables